## 2013
Milestone | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01
Separate TNRS from data loading | bar: 2013-01-01
Obtain and load any additional new data | bar: 2013-01-01; 2013-04-01
Reload existing data in need of refresh | bar: 2013-01-01 to 2013-03-01; 2013-05-01 to 2013-06-01
Data provider validations | bar: 2013-01-01 to 2013-03-01
Final revisions to schema | bar: 2013-01-01 to 2013-04-01; 2013-07-01 to 2013-08-01
Rebuild core database | bar: 2013-02-01 to 2013-03-01; 2013-05-01 to 2013-06-01
Complete analytical database (geoscrubbing, etc.) | bar: 2013-01-01 to 2013-03-01; 2013-06-01
Reload analytical database | bar: 2013-02-01 to 2013-03-01; 2013-05-01 to 2013-06-01
Prepare to rerun species range models | bar: 2013-04-01 to 2013-06-01
Modify scripts to load/refresh individual data sources | bar: 2013-01-01
Switching to new-style import
Importing to normalized VegCore
Adding derived columns
Improve and complete data provider metadata
Automation of attribution and conditions of use
Data provider feedback (data provider pages on website?)
Web interface enhancements (+ page on how to become data provider) | bar: 2013-04-01
Exchange schema. Automated protocol for new BIEN data providers. BIEN website; TDWG standard; publication | bar: 2013-03-01 to 2013-04-01
Finish all documentation | bar: 2013-06-01