## 2013
Milestone | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | later
Switching to new-style import | bar: 2013-07-01 to 2013-08-01
Translate source-specific derived columns to plain SQL | bar: 2013-07-01
Rename staging table columns to VegCore | bar: 2013-07-01
Flatten the datasources | bar: 2013-07-01 to 2013-08-01
Move denormalized validations to stage II | bar: 2013-08-01
Move stage III validations to stage II | bar: 2013-08-01
Adding derived columns | bar: 2013-01-01 to 2013-03-01; 2013-06-01; 2013-08-01 to 2013-09-01
Geoscrubbing (needs re-run and automated pipeline) | bar: 2013-08-01 to 2013-09-01
Attribution and conditions of use | bar: 2013-09-01
Prepare to rerun species range models (Brad) | [10 empty] | • | bar: 2013-04-01 to 2013-06-01
Importing to normalized VegCore | bar: 2013-09-01
Individual datasource refresh (also for normalized VegCore) | bar: 2013-01-01; 2013-09-01
Data provider validations | bar: 2013-01-01 to 2013-03-01; 2013-09-01 to 2013-10-01
Revisions to schema | [10 empty] | • | bar: 2013-01-01 to 2013-04-01; 2013-10-01
Improve and complete data provider metadata | bar: 2013-10-01
Reload existing data in need of refresh (CTFS left) | [10 empty] | • | bar: 2013-01-01 to 2013-03-01; 2013-05-01 to 2013-06-01
Exchange schema. Automated protocol for new BIEN data providers. BIEN website; TDWG standard; publication | [10 empty] | • | bar: 2013-03-01 to 2013-04-01
Web interface enhancements (+ page on how to become data provider) (Brad) | [10 empty] | • | bar: 2013-04-01
Data provider feedback (data provider pages on website?) | [10 empty] | •
Obtain and load any additional new data | [10 empty] | • | bar: 2013-01-01; 2013-04-01
Separate TNRS from data loading | bar: 2013-01-01
Rebuild core database (monthly) | [10 empty] | • | bar: 2013-01-01 to 2013-10-01
Reload analytical database (monthly) | [10 empty] | • | bar: 2013-01-01 to 2013-10-01
Documentation (continuous) | [10 empty] | • | bar: 2013-01-01 to 2013-10-01