## 2013
The purpose of the dots is to show what tasks should be worked on when. In some cases, the number of dots is also proportional to the complexity of the task.
Milestone | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | later
Datasource validations (spot-checking) | bar: 2013-01-01 to 2013-03-01; 2013-07-01 to 2013-10-01
Flatten the datasources to a common schema | bar: 2013-09-01
Aggregated validations (counts) | bar: 2013-09-01 to 2013-10-01
Improve and complete data provider metadata (iPlant can do) | bar: 2013-08-01 to 2013-10-01
Add derived data version info | bar: 2013-08-01 to 2013-09-01
Attribution and conditions of use (iPlant can do) | bar: 2013-09-01
Streamline process of mapping and adding a new datasource | bar: 2013-08-01 to 2013-10-01
Individual datasource refresh (revisit to optimize) | bar: 2013-01-01; 2013-08-01 to 2013-09-01
Individual datasource removal (revisit to optimize) | bar: 2013-01-01; 2013-08-01
Switching to new-style import | bar: 2013-07-01 to 2013-10-01
Translate source-specific derived columns to plain SQL | bar: 2013-07-01 to 2013-09-01
Rename staging table columns to VegCore | bar: 2013-07-01 to 2013-09-01
Move denormalized validations to stage II | bar: 2013-10-01
Move stage III validations to stage II | bar: 2013-10-01
Avoid DB restructuring when ingesting a new datasource | bar: 2013-09-01
Adding derived columns | bar: 2013-01-01 to 2013-03-01; 2013-06-01; 2013-09-01 to 2013-10-01
Geoscrubbing re-run (Jim or iPlant can do) | bar: 2013-09-01 to 2013-10-01
Geoscrubbing automated pipeline (iPlant can do) | bar: 2013-10-01
Prepare to rerun species range models (Brad) | [10 empty] | • | bar: 2013-04-01 to 2013-06-01
Importing to normalized VegCore | [10 empty] | •
Spot-checking | [10 empty] | •
Revisions to schema | [10 empty] | • | bar: 2013-01-01 to 2013-04-01; 2013-07-01 to 2013-10-01
Reload existing data in need of refresh (CTFS left) | [10 empty] | • | bar: 2013-01-01 to 2013-03-01; 2013-05-01 to 2013-06-01
Exchange schema. Automated protocol for new BIEN data providers. BIEN website; TDWG standard; publication | [10 empty] | • | bar: 2013-03-01 to 2013-04-01
Web interface enhancements (+ page on how to become data provider) (Brad) | [10 empty] | • | bar: 2013-04-01
Data provider feedback (data provider pages on website?) | [10 empty] | •
Obtain and load any additional new data (iPlant can help with) | [10 empty] | • | bar: 2013-01-01; 2013-04-01
Separate TNRS from data loading | bar: 2013-01-01
Rebuild core database (monthly) | [10 empty] | • | bar: 2013-01-01 to 2013-10-01
Reload analytical database (monthly) | [10 empty] | • | bar: 2013-01-01 to 2013-10-01
Documentation (continuous) | [10 empty] | • | bar: 2013-01-01 to 2013-10-01