## 2013
The dots show what tasks should be worked on when, but are not necessarily proportional to the complexity of the task.
During week of:
Milestone | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-02 | 2013-09-09 | 2013-09-16 | 2013-09-23 | 2013-09-30 | 2013-10-07 | 2013-10-14 | 2013-10-21 | 2013-10-28 | later
datasource validations (spot-checking) | bar: 2013-01-01 to 2013-03-01; 2013-07-01 to 2013-10-14
flatten the datasources to a common schema | bar: 2013-09-09 to 2013-09-16; 2013-10-07 to 2013-10-14
left-join unvalidated datasources | bar: 2013-09-09 to 2013-09-16
revisions to schema | bar: 2013-01-01 to 2013-04-01; 2013-07-01 to 2013-08-01; 2013-09-09 to 2013-10-14
aggregated validations (counts) | bar: 2013-10-14 to 2013-10-28
simplify process of mapping/adding a new datasource | bar: 2013-08-01; 2013-09-16 to 2013-10-28
switching to new-style import | [17 empty] | • | bar: 2013-07-01 to 2013-08-01; 2013-09-09 to 2013-09-23
translate source-specific derived cols to plain SQL | bar: 2013-07-01 to 2013-08-01; 2013-09-09 to 2013-09-23
rename staging table columns to VegCore | bar: 2013-07-01 to 2013-08-01; 2013-09-09 to 2013-09-23
move denormalized validations to stage II | [17 empty] | •
move stage III validations to stage II | [17 empty] | •
create interactive scripts for each import step | bar: 2013-09-30 to 2013-10-14
individual datasource refresh (revisit to optimize) | bar: 2013-01-01; 2013-08-01; 2013-10-21 to 2013-10-28
individual datasource removal (revisit to optimize) | bar: 2013-01-01; 2013-08-01
separate TNRS from data loading | bar: 2013-01-01
avoid DB restructuring when ingesting a new datasource
documentation testing | bar: 2013-09-02; 2013-09-16 to 2013-10-28
set aside time and funding | bar: 2013-09-02; 2013-09-16 to 2013-09-23
find out amount remaining in BIEN3 budget | bar: 2013-09-16
find a documentation tester | bar: 2013-09-02; 2013-09-16 to 2013-09-30
receive feedback from the documentation tester | bar: 2013-10-07 to 2013-10-28
fix issues uncovered | bar: 2013-10-14 to 2013-10-28
usability testing | [17 empty] | • | bar: 2013-09-02 to 2013-09-09; 2013-09-30 to 2013-10-14
find missing columns | [17 empty] | • | bar: 2013-09-02
add any missing columns | [17 empty] | • | bar: 2013-09-09; 2013-09-30 to 2013-10-14
geoscrubbing re-run (Jim or iPlant can do) | bar: 2013-09-09; 2013-10-07 to 2013-10-14
data provider metadata (iPlant can do) | [17 empty] | • | bar: 2013-08-01; 2013-10-21 to 2013-10-28
attribution and conditions of use (Brad/Brian/Bob) | [17 empty] | • | bar: 2013-10-21 to 2013-10-28
add derived data version info | [17 empty] | • | bar: 2013-08-01
reload core & analytical database (monthly) | bar: 2013-01-01 to 2013-08-01; 2013-09-30; 2013-10-21
documentation (continuous) | [17 empty] | • | bar: 2013-01-01 to 2013-10-28
adding derived columns | [17 empty] | • | bar: 2013-01-01 to 2013-03-01; 2013-06-01
geoscrubbing automated pipeline (iPlant can do) | [17 empty] | •
prepare to rerun species range models (Brad) | [17 empty] | • | bar: 2013-04-01 to 2013-06-01
importing to normalized VegCore | [17 empty] | •
spot-checking | [17 empty] | •
reload existing data in need of refresh (CTFS left) | [17 empty] | • | bar: 2013-01-01 to 2013-03-01; 2013-05-01 to 2013-06-01
exchange schema. automated steps for new BIEN data providers. BIEN website; TDWG standard; publication | [17 empty] | • | bar: 2013-03-01 to 2013-04-01
web interface enhancements (+ page on how to become data provider) (Brad) | [17 empty] | • | bar: 2013-04-01
data provider feedback (pages on website?) | [17 empty] | •
obtain & load additional new data (iPlant can help) | [17 empty] | • | bar: 2013-01-01; 2013-04-01