## 2013
The dots show what tasks should be worked on when, but are not necessarily proportional to the task complexity.
Milestone week of: | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-02 | 2013-09-09 | 2013-09-16 | 2013-09-23 | 2013-09-30 | 2013-10-07 | 2013-10-14 | 2013-10-21 | 2013-10-28 | 2013-11-04 | 2013-11-11 | 2013-11-18 | 2013-11-25 | 2013-12-02 | 2013-12-09 | 2013-12-16 | later
usability testing | [24 empty] | ◦ | bar: 2013-09-02 to 2013-09-09; 2013-10-14 to 2013-12-16
find scientists who want to use BIEN3 data | bar: 2013-10-14; 2013-11-04 to 2013-11-11
ask scientists which columns they need | bar: 2013-10-14 to 2013-10-21; 2013-11-04 to 2013-11-18
determine which columns are missing | bar: 2013-09-02; 2013-10-14; 2013-10-28 to 2013-11-18
add missing columns | 2013-09-09: ✓; 2013-09-30: ☑; 2013-10-07: ☑; 2013-10-14: ☑; 2013-10-21: ☑; 2013-10-28: ☑; 2013-11-04: ☑; 2013-11-18: ☑; 2013-12-02: ☑; 2013-12-09: •; 2013-12-16: • | •
geoscrubbing | bar: 2013-09-09; 2013-09-30 to 2013-10-28
geoscrubbing re-run (Paul@iPlant) | bar: 2013-10-14
geoscrubbing data reload | bar: 2013-10-14 to 2013-10-21
spot-check reloaded geoscrubbing data | bar: 2013-10-14; 2013-10-28
add occurrenceID | bar: 2013-10-21 to 2013-11-04
attribution/conditions of use | bar: 2013-10-14; 2013-11-11; 2013-12-02
validate the scientists' extracts | [24 empty] | • | bar: 2013-10-21 to 2013-11-04; 2013-11-18; 2013-12-09 to 2013-12-16
provide scientists with their requested data | [24 empty] | • | bar: 2013-10-14 to 2013-11-04; 2013-11-18
Brian Enquist's Canadensys extract | bar: 2013-10-21 to 2013-10-28
datasource validations | ✓ | ✓ | ✓ |  |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ☑ | ☑ | ☑ | ☑ | ☑ | ☑ | ☑ | ☑ | ◦ | ◦ | ◦
revisions to VegBIEN schema | [24 empty] | • | bar: 2013-01-01 to 2013-04-01; 2013-07-01 to 2013-08-01; 2013-09-09 to 2013-10-14; 2013-10-28 to 2013-11-11; 2013-12-09 to 2013-12-16
fix issues and critical feature requests | bar: 2013-10-14 to 2013-12-09
VegBank | bar: 2013-10-14 to 2013-10-28
CVS | bar: 2013-10-21; 2013-11-18 to 2013-12-02
switch to new-style import | bar: 2013-11-18 to 2013-11-25
src-specific derived cols → plain SQL | bar: 2013-11-18 to 2013-11-25
staging table columns → VegCore | bar: 2013-11-25
left-join it | bar: 2013-11-25
VegBank-related changes | bar: 2013-11-18 to 2013-12-02
Madidi | bar: 2013-12-09
ARIZ | bar: 2013-12-09
U | bar: 2013-12-09
TEX | bar: 2013-12-09
prepare 1st-round extracts | bar: 2013-11-25 to 2013-12-16
CVS | bar: 2013-11-25
create validation subset | bar: 2013-11-25
refresh | bar: 2013-12-09
create extract | bar: 2013-11-25
FIA | bar: 2013-12-02 to 2013-12-09
decide which columns to validate | bar: 2013-12-02
create validation subset | bar: 2013-12-02
create extract | bar: 2013-12-02 to 2013-12-09
MO | bar: 2013-12-09
GBIF | bar: 2013-12-09
UNCC | bar: 2013-12-16
prepare 2nd-round extracts | bar: 2013-10-07; 2013-12-09
VegBank | bar: 2013-10-07
Madidi | bar: 2013-12-09
ARIZ | bar: 2013-12-09
U | bar: 2013-12-09
TEX | bar: 2013-12-09
data providers review extracts | [24 empty] | ◦ | bar: 2013-11-04 to 2013-11-11; 2013-12-02 to 2013-12-16
VegBank | bar: 2013-11-04 to 2013-11-11
CVS | bar: 2013-12-02
Madidi | bar: 2013-12-09
FIA | bar: 2013-12-09
MO | bar: 2013-12-16
GBIF | [24 empty] | ◦
UNCC | [24 empty] | ◦
ARIZ | bar: 2013-12-16
U | bar: 2013-12-16
TEX | bar: 2013-12-16
fix new issues uncovered | [24 empty] | ◦ | bar: 2013-11-04 to 2013-11-11; 2013-12-09 to 2013-12-16
VegBank | bar: 2013-11-04 to 2013-11-11
CVS | bar: 2013-12-09
Madidi | bar: 2013-12-16
FIA | bar: 2013-12-16
MO | [24 empty] | •
GBIF | [24 empty] | •
UNCC | [24 empty] | •
ARIZ | [24 empty] | •
U | [24 empty] | •
TEX | [24 empty] | •
prepare additional-round extracts | [24 empty] | • | bar: 2013-10-28
VegBank | bar: 2013-10-28
fix non-critical feature requests | [24 empty] | ◦
VegBank | [24 empty] | •
CVS | [24 empty] | •
Madidi | [24 empty] | •
ARIZ | [24 empty] | •
aggregated validations (counts) | [24 empty] | • | bar: 2013-12-02
simplify process of adding a new datasource | [24 empty] | ◦ | bar: 2013-12-02
create interactive scripts for each import step | [24 empty] | • | bar: 2013-09-23; 2013-12-02
individual datasource refresh (optimize) | [24 empty] | • | bar: 2013-01-01; 2013-08-01; 2013-12-02
individual datasource removal (revisit to optimize) | bar: 2013-01-01; 2013-08-01
separate TNRS from data loading | bar: 2013-01-01
avoid DB restructuring when ingesting a new datasource
documentation testing | [24 empty] | ◦ | bar: 2013-09-02; 2013-09-23; 2013-10-14; 2013-12-02
set aside time and funding | bar: 2013-09-02; 2013-09-23; 2013-10-14
find out amount remaining in BIEN3 budget | bar: 2013-09-23
find a documentation tester | [24 empty] | ◦ | bar: 2013-09-02; 2013-12-02
receive feedback from documentation tester | [24 empty] | ◦ | bar: 2013-12-02
fix issues uncovered | [24 empty] | • | bar: 2013-12-02
simplify import process for easier maintainability | [24 empty] | ◦ | bar: 2013-08-01; 2013-09-23
switching to new-style import | [24 empty] | • | bar: 2013-07-01 to 2013-08-01; 2013-09-09; 2013-12-02
flatten the datasources to a common schema | [24 empty] | • | bar: 2013-09-09 to 2013-09-16
move denormalized validations to stage II | [24 empty] | •
move stage III validations to stage II | [24 empty] | •
geoscrubbing automated pipeline | [24 empty] | ◦ | bar: 2013-10-14 to 2013-11-04
build pipeline (Paul@iPlant) | bar: 2013-10-14 to 2013-10-28
test pipeline | bar: 2013-11-04
validate geoscrubbing results | bar: 2013-11-04
integrate pipeline into import process | [24 empty] | • | bar: 2013-11-04
reload core & analytical database | [24 empty] | • | bar: 2013-01-01 to 2013-08-01; 2013-10-07 to 2013-10-14; 2013-10-28 to 2013-11-04; 2013-11-25 to 2013-12-16
documentation (continuous) | [24 empty] | • | bar: 2013-01-01 to 2013-12-16
revisions to normalized VegCore | [24 empty] | • | bar: 2013-03-01 to 2013-04-01; 2013-07-01 to 2013-08-01; 2013-09-09 to 2013-10-28; 2013-12-09 to 2013-12-16
create high-level workflow diagram | [24 empty] | •
data provider metadata | [24 empty] | • | bar: 2013-08-01
add derived data version info | [24 empty] | • | bar: 2013-08-01
adding derived columns | [24 empty] | • | bar: 2013-01-01 to 2013-03-01; 2013-06-01
prepare to rerun species range models (Brad) | [24 empty] | • | bar: 2013-04-01 to 2013-06-01
importing to normalized VegCore | [24 empty] | •
spot-checking | [24 empty] | •
reload existing data in need of refresh | [24 empty] | • | bar: 2013-01-01 to 2013-03-01; 2013-05-01 to 2013-06-01
load BIEN2 exports directly from raw data | [24 empty] | •
CTFS | [24 empty] | •
exchange schema. automated steps for new BIEN data providers. BIEN website; TDWG standard; publication | [24 empty] | • | bar: 2013-03-01 to 2013-04-01
web interface enhancements (+ page on how to become data provider) (Brad) | [24 empty] | • | bar: 2013-04-01
data provider feedback (pages on website?) | [24 empty] | •
obtain & load additional new data (iPlant) | [24 empty] | • | bar: 2013-01-01; 2013-04-01
Legend: • ✓ task
◦ ☑ timespan