## 2013
Milestone | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01
Separate TNRS from data loading | bar: 2013-01-01
Obtain and load any additional new data | bar: 2013-01-01; 2013-04-01
Reload existing data in need of refresh | bar: 2013-01-01
Data provider validations | bar: 2013-01-01 to 2013-02-01
Final revisions to schema | bar: 2013-01-01 to 2013-02-01
Rebuild core database | bar: 2013-02-01
Complete analytical database (geoscrubbing, etc.) | bar: 2013-01-01 to 2013-03-01
Reload analytical database | bar: 2013-03-01
Rerun species range models | bar: 2013-03-01
Modify scripts to load/refresh individual data sources | bar: 2013-01-01
Improve and complete data provider metadata | bar: 2013-04-01
Automation of attribution and conditions of use | bar: 2013-04-01 to 2013-05-01
Data provider feedback (data provider pages on website?) | bar: 2013-04-01 to 2013-06-01
Web interface enhancements (+ page on how to become data provider) | bar: 2013-04-01 to 2013-05-01
Exchange schema. Automated protocol for new BIEN data providers. BIEN website; TDWG standard; publication | bar: 2013-05-01 to 2013-06-01
Finish all documentation | bar: 2013-05-01 to 2013-06-01